## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Data Loading & Text Preprocessing | Data is loaded, cleaned and normalized. | 1 | The data is loaded, cleaned, analysed and normalised, ready to be vectorized. | SHOULD HAVE | The dataset should not have any duplicates or null values creating noise. | Aparna | 3- Completed
Feature Extraction - TF-IDF and Embeddings | Several Conversion techniques were analysed. | 2 | Several vectorizers and embedding techniques were analyzed, TF-IDF was chosen. | MUST HAVE | The dataset must be vectorized properly. | Aparna, Lithikha B | 3- Completed
Model Building - Train Models | 6 different models including Logistic Regression. | 3 | Built Linear SVC, MultinomialNB, Random Forest, Gradient Boosting, and XGBoost. | SHOULD HAVE | All necessary models imported and ready to be put in a pipeline. | Lithikha B | 3- Completed
Model Evaluation | Accuracy, Precision, Recall, and F1-Score analyzed. | 4 | The evaluation metrics are calculated, and the models are compared. | MUST HAVE | Pipelined all the models and displayed the final graph. | Lithikha B | 3- Completed
Post-evaluation - Confusion Matrix | Misclassifications visualized in a heatmap. | 5 | Visualizing the confusion matrix to analyze model misclassifications. | MUST HAVE | Heatmap displays exact values of false positives and negatives. | Aarya Chavan, Aparna | 3- Completed
Performance Improvement | Optimized model using hyperparameter tuning. | 6 | Used GridSearchCV for Logistic Regression optimization. | MUST HAVE | Compared confusion matrix of base and optimized models for improvement. | Aarya Chavan, Aparna | 3- Completed
Deployment Readiness |  | 7 | Model prepared for API deployment. | MUST HAVE | Ready for integration with API services. | Axit | 3- Completed
Final Report Preparation |  | 8 | Documented the entire model development process and sentiment analysis insights. | MUST HAVE | Final project report completion. | Axit | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 2024-11-10 | importing the dataset form kaggle | downloaded the dataset from kaggle plaftform
1 | 2024-11-11 | checking wheather any missing and duplications | used the fuctions of missing and duplicate values and romoved them
1 | 2024-11-14 | data cleaning ,removes the keywords and decreses the accuracy. | text cleaning process is scrunitized
1 | 2024-11-18 | feature extraction and tfidf vectorizer and emeddings | used the relevent features for modeling,applied tfidf and word embeddings for text classifications
2 | 21/11/2024 | Model Building - Train Logistic Regression model for sentiment classification | After evaluating multiple classifiers for sentiment analysis,Logistic Regression and Linear SVC achieve the highest accuracy, both exceeding 87%.
2 | 24/11/2024 | Comprehensive evaluation report with accuracy, F1-score, and confusion matrix. | we decided Logistic Regression has superior accuracy, computational efficiency, and ability to generalize well.
3 | 14/11/2024 | Confusion Matrix Visualization | Identify patterns in false positives/negatives to understand model weaknesses.
3 | 16/11/2024 | Hyperparameter tuning and re-evaluation | Use techniques like GridSearchCV or RandomizedSearchCV to optimize model hyperparameters.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 26 | 5.5 | 4.5 | 4.5 | 4.5 | 4 | 2 | 2 | 0 | 2 | 3 | 1.5 | 3 | 3 | 1
SPRINT 1 BACKLOG
| 1 | Data is Loaded, Preprocessed and Analysed. Added Count, TF-TDF and Hashing Vectorizer. Also added Embedding too. | 2024-10-29 | 2024-11-20 | Aparna, Lithikha B | Coding | 3- Completed | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 0.5 | 2 | 2 | 0
| 2 | Trained Logistic Regression and multiple models for sentiment classification. Prepared a comprehensive evaluation report with accuracy, F1-score, and confusion matrix. | 2024-11-21 | 2024-11-25 | Lithikha B | Build | 3- Completed | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Visualization report on misclassifications and confusion matrix analysis.Optimized model with improved hyperparameters and performance metrics. | 2024-12-13 | 2024-12-19 | Aarya Chavan, Aparna | Design | 3- Completed | 11 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| 4 | Deployment-ready model packaged for integration with API services. Final project report detailing approach, results, and sentiment insights. | 2024-12-20 | 2024-12-26 | Axit Gadhiya | Deployment & Documentation | 3- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2024-11-08 | 2024-11-20 | Aparna | 2024-11-08 | 2024-11-16 |  | Basic Model with TF-IDF vectorizer was done.
2 | 1 | 2024-11-08 | 2024-11-20 | Lithikha B | 2024-11-17 | 2024-11-19 |  | Count & Hashing Vectorizer, Word2Vec was added
3 | 2 | 2024-11-21 | 2024-11-25 | Lithikha B | 2024-11-21 | 2024-11-25 |  | Built and Evaluated 6 different models, and an evaluation report is done.
4 | 3 | 2024-12-13 | 2024-12-16 | Aarya chavan , Aparna | 2024-12-13 | 2024-12-15 |  | Visualize confusion matrices for each model to analyze misclassifications.
5 | 3 | 2024-12-16 | 2024-12-19 | Aarya chavan , Aparna | 2024-12-16 | 2024-12-19 |  | Retrain and re-evaluate models with the best hyperparameters to improve performance.
6
7